## Instructions
Column | Instructions For Completing This Document
Complete the Project Name, Organization, OIT Project Manager Name
For each lesson learned entry, complete the following:
A | ID: Enter a unique ID number.
B | Date Identified: Enter identification date of Lessons Learned / Best Practice.
C | Entered By: Enter the individual's name who identified the Lesson Learned / Best Practice.
D | Category: Select from the dropdown; populated with project knowledge areas.
E | Lesson Learned / Best Practice: Describe Lesson Learned / Best Practice.
F | Recommendation: Enter recommendations, corrective action to help guide future project managers or use in future projects.
Column | Instructions for Dropdown Content Menu
D | Highlight cell D From the file menu click "Data" tab --> "Data Tools" group -->"Data Validation" option. In the pop-up window change the content of the source field as needed.
Lessons Learned Guidance
It is important that the lessons learned approach is covered in the initial stages of project planning. The lessons learned log is a living document through the duration of the project until project closeout. In addition to project activities, use Retrospective Meeting Minutes as reference for lessons learned. Lessons Learned may be used as part of new project planning for similar projects to determine what problems occurred and how those problems were handled and may be avoided in the future. Additionally, capture what went well with the project and why (Best Practice), so that other project managers may capitalize on these actions.
DOCUMENT REVISION HISTORY VERSION: 1.0 DATE: 11/02/2020 CHANGE DESCRIPTION: Created new artifact; reflects FNS Agile SDLC processes and comply with Section 508 standards.

## Lessons Learned Log
LESSONS LEARNED LOG
Project Name:
Organization:
OIT Project Manager:
ID | Date Identified | Entered By | Category | Lesson Learned / Best Practice | Recommendation
1 | 2020-09-21 | John Doe | Scope | Stakeholders continuously tried adding to the backlog throughout the project. | The PM must have an approval process from the Product Owner for any proposed scope changes.
2 | 2020-10-15 | Mary Smith | Resources | There was no plan for providing awards and recognition to team members. | The PM should institute and communicate an awards/recognition program for every project.