## Instructions
About this workbook
This workbook contains two tabs: Roadmap Data Instructions Roadmap Data Tab Column A - Enter Theme, Epic, Function, Domain. Column B: Row 1 - Enter target timeline series (e.g. federal government fiscal year, calendar fiscal year) Row 2 - Enter timeboxed series (e.g. Release, Sprint) Row 3, Row 4 (nth) - Enter milestone, task or activity. To remove these instructions, simply delete this tab.
DOCUMENT REVISION HISTORY VERSION: 1.0 DATE: 11/02/2020 CHANGE DESCRIPTION: Created new artifact; reflects FNS Agile SDLC processes and comply with Section 508 standards.

## Roadmap
| 2021 - Q1 | 2021 - Q2 | 2021 - Q3 | 2021 - Q4 | 2022 - Q1
| RELEASE 1 | RELEASE 2 | RELEASE 3 | RELEASE 4 | RELEASE 5
3rd Party Integration INTEGRATION | Develop User Stories | Develop Salesforce API | Product Prototype | Integrated Prototype
| Develop Slack API | Test Salesfore API | Develop Teams API | Deploy to Production
| Test Slack API |  | Test Teams API
MOBILE INTEGRATION | Create Mobile Mock Up | Story Review | iOS Upgrade | Ticketing App
| Develop Beta Mobile App | Demo | Mobile Service Service Interface
| Tech Analysis | Integrated Prototype
USER EXPERIENCE | Wireframe | Feature Design | Site Test | Style Guide Development
| Surface Design | UX Audit | Regression Testing
UX Templates
Feature Design